**Online Marketplace Documentation & Breakdown**

Code Structure & Basic Setup

**Laravel Setup** - (2 days)

Laravel Setup with basic minimal authentication modules installation and modular dependencies along with git flow and tasks management regarding the project.

**PHASE 1 - (2 weeks)**

**Html5 Conversions for designs - Wireframes -** (2 weeks)

**1 -** 26 pages unique structures - (2 weeks for html conversion along with responsiveness checks and testing for html quality)

**PHASE 2 - (3 weeks & 1 day)**

**User Cases / Admin cases Pages**

**User registration / Signup Pages - Login Pages (2 days)**

**1 - User Profile Module**

* **Profile - public**
  + **Please define all fields for user profile here - (3 days)**
  + **We are missing the profile page & edit profile page design as well please provide wireframe for that**
  + **Mission board functionality (1 day)**
* **User Profile Listings - public - (3 days)**
  + **Dashboard for User**
  + **Listings for items for auction - including bid functionality**
  + **Similar listings items for auction - including bid functionality**
* **Karma - public**
  + **Functionality for feedback after buying / selling karma listings and reply back from the owner (5 days)**
  + **Receive as buyer and receive as seller for feedback & listings**
* **Bookmarked - public - (1 days)**
  + **Listings for all auction bookmarked for oversee or interested in**
* **Social - public - (1 day)**
  + **User you follow and users follow you functionality**
  + **Including the listings**
* **Draft - private - (1 day)**
  + **Auction which are listed as draft, and can be used later.**
* **My cards - private**
  + **Please provide more information regarding this**
* **Message functionality - (3 days)**
  + **Send / receive functionality in between users privately**
* **My Order - (2 days)**
  + **Items which are bought from auction**

**PHASE 3 - (4 weeks)**

**OverALL Auction functionality**

**1 - New Auction - (4 days)**

* Fixed price
* Flexible price - bidding based

And all other attributes available in design / wireframes.

Including edit auction feature as well.

**2 - Auction Detail Page - dashboard with bidding functionality - (8 days)**

**It includes everything which in wireframe including the chart**

**3 - Homepage - Public - (9 days)**

* Auction latest -
  + Detail page for all listings
* Sales Latest
  + Detail page for all listings
* Following Social User Listings
  + Detail page for all listings
* Listings Similar
  + Detail page for all listings
* Trending OverAll based on data
  + Detail page for all listings

**4 - Homepage - Logged In - (2 day)**

**5 - Search Page - (3 days)**

**Filter by**

* **Type**
* **Condition**
* **Language**
* **Condition**
* **Edition**
* **And if there are more please describe ?**

**We will use the same design layout and can copy a few things from the home page to save time.**

This is overall estimations, which is a close estimate to overall we think is best, if anything got changed on the spot, or requirement change will be subject to change in time.

Please help us to improve this document, if we miss something. It will be helpful to discuss in start, to have everything on table.